## Sheet4
Row Labels | Count of Task Name
Completed | 9
In Progress | 16
Not Started | 21
Grand Total | 46

## Sheet6
Row Labels | Count of Task Name
Consulting | 3
Customer Svc | 3
Development | 3
Engineering | 3
Events | 3
Financial | 3
Logistics | 3
Marketing | 4
Operations | 3
Product Dev | 3
Production | 3
Research | 3
Sales | 3
Support | 3
Training | 3
Grand Total | 46

## Sheet7
Row Labels | Average of Progress
Consulting | 20%
Customer Svc | 66.67%
Development | 33.33%
Engineering | 6.667%
Events | 10%
Financial | 62.67%
Logistics | 50%
Marketing | 55.75%
Operations | 13.33%
Product Dev | 59.33%
Production | 10%
Research | 16.67%
Sales | 49.33%
Support | 66.67%
Training | 26.67%
Grand Total | 36.89%

## Sheet8
Row Labels | Count of Task Name
Aaron | 1
Alice | 1
Bella | 1
Bob | 1
Calvin | 1
Charlie | 1
Daisy | 1
Diane | 1
Edward | 1
Ethan | 1
Fiona | 2
Gabriel | 1
Gary | 1
Hannah | 1
Helen | 1
Ian | 1
Isaac | 1
Jane | 1
Julia | 1
Kevin | 1
Kyle | 1
Laura | 1
Mark | 2
Mike | 1
n Nancy | 1
Nathan | 1
Olivia | 1
Oscar | 1
Patricia | 1
Peter | 1
Quentin | 1
Quinn | 1
Rachel | 2
Sam | 2
Tim | 1
Tom | 1
Ursula | 1
Victor | 1
Wendy | 1
Xavier | 1
Yvette | 1
Zoe | 1
Grand Total | 46

## lakshay
|  | Project Management Data | [6 empty] | Project And Task Management Dashboard
Project Name | Task Name | Assigned to | Start Date | Days Required | End Date | Progress | task status | Total Project | Total Task | Completed Task | Pending Task | Average Progress
Marketing | Market Research | Alice | 2024-01-01 | 13 | 1/14/2024 | 78% | In Progress | 15 | 46 | 9 | 37 | 36.89%
Marketing | Content Creation | Bob | 1/14/2024 | 14 | 1/28/2024 | 100% | In Progress
Marketing | Social Media Planning | Charlie | 1/28/2024 | 22 | 2/19/2024 | 45% | Completed
Marketing | Campaign Analysis | Daisy | 2/18/2024 | 25 | 3/14/2024 | 0% | In Progress
Product Dev | Prototype Development | Ethan | 2024-02-01 | 18 | 1/20/2024 | 100% | Not Started
Product Dev | Quality Assurance | Fiona | 1/20/2024 | 10 | 1/30/2024 | 78% | Completed
Product Dev | User Interface Design | Gabriel | 2024-04-02 | 25 | 2/29/2024 | 0% | In Progress
Customer Svc | Service Improvement | Hannah | 2024-01-02 | 22 | 2/23/2024 | 100% | Not Started
Customer Svc | Ticket Resolution | Ian | 2/24/2024 | 25 | 3/20/2024 | 100% | Completed
Customer Svc | Customer Feedback | Julia | 3/21/2024 | 30 | 4/20/2024 | 0% | Completed
Financial | Budget Analysis | Kevin | 2024-02-02 | 22 | 2/24/2024 | 10% | Not Started
Financial | Financial Reporting | Mark | 2/13/2024 | 21 | 2024-09-02 | 78% | In Progress
Financial | Investment Planning | Mark | 3/19/2024 | 25 | 4/13/2024 | 100% | In Progress
Research | Market Trends Analysis | Nathan | 2024-02-01 | 23 | 1/25/2024 | 50% | Completed
Research | Data Collection | Olivia | 1/26/2024 | 32 | 2/27/2024 | 0% | In Progress
Research | Research Paper Writing | Peter | 2/28/2024 | 27 | 3/26/2024 | 0% | Not Started
Development | Software Development | Quinn | 2024-02-01 | 36 | 2024-07-02 | 100% | Not Started
Development | Feature Enhancement | Rachel | 2024-08-02 | 34 | 3/13/2024 | 0% | Completed
Development | Code Review | Sam | 3/14/2024 | 30 | 4/13/2024 | 0% | Not Started
Production | Manufacturing | Tim | 2024-03-01 | 47 | 2/19/2024 | 30% | Not Started
Production | Quality Control | Ursula | 2/17/2024 | 27 | 3/15/2024 | 0% | In Progress
Production | Packaging Design | Victor | 3/14/2024 | 22 | 2024-05-04 | 0% | Not Started
Sales | Lead Generation | Wendy | 2024-03-01 | 60 | 2024-03-03 | 70% | Not Started
Sales | Client Meetings | Xavier | 2024-06-01 | 20 | 1/26/2024 | 78% | In Progress
Sales | Contract Negotiation | Yvette | 2024-03-02 | 35 | 2024-09-03 | 0% | In Progress
Support | Technical Support | Zoe | 2024-01-01 | 25 | 1/26/2024 | 100% | Not Started
Support | Bug Fixes | Aaron | 1/27/2024 | 31 | 2/27/2024 | 100% | Completed
Support | Software Updates | Bella | 2024-02-03 | 22 | 3/24/2024 | 0% | Completed
Operations | Process Optimization | Calvin | 2024-03-01 | 30 | 2024-02-02 | 40% | Not Started
Operations | Inventory Management | Diane | 2024-03-02 | 25 | 2/28/2024 | 0% | In Progress
Operations | Facility Maintenance | Edward | 2/29/2024 | 20 | 3/20/2024 | 0% | Not Started
Consulting | Strategic Planning | Fiona | 2024-02-01 | 35 | 2024-06-02 | 60% | Not Started
Consulting | Market Expansion | Gary | 2024-02-02 | 32 | 2024-05-03 | 0% | In Progress
Consulting | Client Advisory | Helen | 2024-06-03 | 25 | 3/31/2024 | 0% | Not Started
Training | Employee Training | Isaac | 2024-04-01 | 27 | 1/31/2024 | 80% | Not Started
Training | Certification Programs | Jane | 1/28/2024 | 30 | 2/27/2024 | 0% | In Progress
Training | Skill Development | Kyle | 2/28/2024 | 22 | 3/21/2024 | 0% | Not Started
Events | Event Planning | Laura | 2024-03-01 | 25 | 1/28/2024 | 30% | Not Started
Events | Conference Management | Mike | 2024-03-02 | 20 | 2/23/2024 | 0% | In Progress
Events | Sponsorship Coordinatio | n Nancy | 2/24/2024 | 35 | 3/30/2024 | 0% | Not Started
Logistics | Supply Chain Management | Oscar | 2024-03-01 | 25 | 1/28/2024 | 50% | Not Started
Logistics | Transportation Planning | Patricia | 1/29/2024 | 30 | 2/28/2024 | 100% | In Progress
Logistics | Inventory Optimization | Quentin | 3/29/2024 | 20 | 4/18/2024 | 0% | Completed
Engineering | Product Design | Rachel | 2024-02-01 | 25 | 1/27/2024 | 20% | Not Started
Engineering | System Integration | Sam | 2024-02-02 | 22 | 2/24/2024 | 0% | In Progress
Engineering | Prototype Testing | Tom | 2/23/2024 | 27 | 3/21/2024 | 0% | Not Started
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.